## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Project Initiation
Gather business metrics to baseline sales and customer volume and velocity | Based on previous project |  |  | 1 | Deanna
Research data points to track using the tablets | Based on previous project |  |  | 7 | Deanna
Align and evaluate stakeholders | Based on previous project |  |  | 2 | Peta
Confer with stakeholders regarding custom branding and design. | Based on previous project |  |  | 1 | Seydou
Finalize budget with managment |  |  |  | 1 | Peta
Schedule meetings with GM regarding anything that may affect tips |  |  |  | 1 | Deanna
Finalize project charter | Based on previous project |  |  | 4 | Peta
Schedule kick off meeting | Based on previous project |  |  | 0 | Peta
Milestone: Selection, Installation, and Integration of Tablets
Work on the database for menu items and coupons |  |  |  | 14 | Carter
Research compatible tablets from at least 5 vendors that can be integrated with current systems | Based on previous project |  |  | 4 | Seydou
Research extent of installation |  |  |  | 1 | Seydou
Test compatible tablets with current systems |  |  |  | 1 | Seydou
Report on tablet peformance and recommend optimal tablet |  |  |  | 1 | Seydou
Generate quotes and review costs of tablet considerations |  |  |  | 0 | Seydou
Finalize tablet choice |  |  |  | 0 | Deanna
Create contract and statement of work for vendor |  |  |  | 1 | Peta
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  |  |  | 1 | Deanna
Create troubleshoot / support plan |  |  |  | 2 | Seydou
Work with vendor to schedule electrician |  |  |  | 0 | Peta
Order tablets | Seydou was confident with estimate if tablets are in stock. However, noted that tablets got delayed by a few days with another customer. |  |  | 10 | Deanna
Wiring of tablets | Notify GMs when their locations need to close for wiring, Check with electrician on whether mornings or afternoons work better with their schedule |  |  | 2 | Deanna
Install and integrate tablets with current system | Need updates for current POS system |  |  | 3 | Seydou
Upload database for menu items and coupons |  |  |  | 1 | Seydou
Milestone: Develop and Launch Employee Training Program
Create training materials and program for staff regarding tablet operation. |  |  |  | 7 | Deanna
Train managers for rollout, operations, and troubleshooting | Separate days for each location |  |  | 2 | Seydou
Train waitstaff for rollout, operations, and troubleshooting | Separate days for each location |  |  | 1 | Seydou
Milestone: Testing of Tablet Reliability and Launch
Create launch day plan |  |  |  | 0 | Peta
Invite friends and family for testing tablet use and reliability | Includes invitation and confirmation for attendance |  |  | 2 | Peta
Launch day |  |  |  | 0 | Peta

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Project Initiation
Gather business metrics to baseline sales and customer volume and velocity | Based on previous project | 1
Research data points to track using the tablets | Based on previous project | 7
Align and evaluate stakeholders | Based on previous project | 2
Confer with stakeholders regarding custom branding and design. | Based on previous project | 1
Finalize budget with managment |  | 1
Schedule meetings with GM regarding anything that may affect tips |  | 1
Finalize project charter | Based on previous project | 4
Schedule kick off meeting | Based on previous project | 0
Milestone: Selection, Installation, and Integration of Tablets
Work on the database for menu items and coupons | Carter | 14 | 7 | 12 | 14 | L
Research compatible tablets from at least 5 vendors that can be integrated with current systems | Based on previous project | 4
Research extent of installation |  | 1
Test compatible tablets with current systems |  | 1
Report on tablet peformance and recommend optimal tablet |  | 1
Generate quotes and review costs of tablet considerations |  | 0
Finalize tablet choice |  | 0
Create contract and statement of work for vendor |  | 1
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  | 1
Create troubleshoot / support plan |  | 2
Work with vendor to schedule electrician |  | 0
Order tablets | Seydou was confident with estimate if tablets are in stock. However, noted that tablets got delayed by a few days with another customer. | 10 | 7 | 10 | 12 | H
Wiring of tablets | Notify GMs when their locations need to close for wiring, Check with electrician on whether mornings or afternoons work better with their schedule | 2 | 3 | 4 |  | M
Install and integrate tablets with current system | Need updates for current POS system | 3 | 3 | 4 | 5 | L
Upload database for menu items and coupons |  | 1 | 1 |  |  | L
Milestone: Develop and Launch Employee Training Program
Create training materials and program for staff regarding tablet operation. |  | 7 | 7 | 8 | 9
Train managers for rollout, operations, and troubleshooting | Separate days for each location | 2 | 1 | 3 | 5 | M
Train waitstaff for rollout, operations, and troubleshooting | Separate days for each location | 1 | 1 | 2 | 3 | L
Milestone: Testing of Tablet Reliability and Launch
Create launch day plan |  | 0
Invite friends and family for testing tablet use and reliability | Includes invitation and confirmation for attendance | 2
Launch day |  | 0

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | 8 minutes wait time for appetizers between order and delivery | How long do customers have to wait for appetizers to arrive from the time they order? | Wait time for appetizers should be less than 8 minutes. | FALSE
Effectiveness | 12 to 15 minutes wait time for entrees between order and delivery | How long do customers have to wait for entrees to arrive from the time they order? | Wait time for entrees should be within 12-15 minutes. | FALSE
Ease of Use | One minute checkout time by ensuring checkout process is seamless and easy to navigate | Do the customers find the tablets convenient and easy to use? | Time spent from pressing check out button to completing the transaction takes less than 1 minute | FALSE
Effectiveness | 98% order accuracy for customer orders | Are the customers receiving correct orders? | 98% order accuracy for customer orders | FALSE
Customer satisfaction | 10 minute average wait time for customers to be seated (lobby wait time) | Do the customers feel that they are seated fast enough? | Average wait time for customers starting from check-in should be less than 10 minutes | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
8 minutes wait time for appetizers between order and delivery | How long do customers have to wait for appetizers to arrive from the time they order? | Wait time for appetizers should be less than 8 minutes. | Have you visited Sauce & Spoon before? | Yes/No | Yes | No
12 to 15 minutes wait time for entrees between order and delivery | How long do customers have to wait for entrees to arrive from the time they order? | Wait time for entrees should be within 12-15 minutes. | How often do you visit Sauce & Spoon? | Multiple choice | Once a month | Twice a month | Weekly | Once every three months | Once every six months
One minute checkout time by ensuring checkout process is seamless and easy to navigate | Do the customers find the tablets convenient and easy to use? | Time spent from pressing check out button to completing the transaction takes less than 1 minute | Was your current visit better than your last? | True/False | True | False
98% order accuracy for customer orders | Are the customers receiving correct orders? | 98% order accuracy for customer orders | How do you feel about our customer service? | Multiple choice | Very dissatisfied | Dissatisfied | Neutral | Satisfied | Very satisfied
10 minute average wait time for customers to be seated (lobby wait time) | Do the customers feel that they are seated fast enough? | Average wait time for customers starting from check-in should be less than 10 minutes | How can we serve you better? | Open-ended | Open-ended
|  |  | Did you use the tablets for order and check out? | Yes/No | Yes | No
|  |  | Did the tablets make you feel more comfortable with dining in? | Yes/No | Yes | No
|  |  | How convenient was it to use the tablets to order and to checkout on a scale of 1 - 5 with 5 being the highest? | Scaled | 1 | 2 | 3 | 4 | 5
|  |  | Did your orders using the tablets arrive as expected? | Yes/No | Yes | No
|  |  | How did the tablets help in understanding our menu offerings on a scale of 1 - 5 with 5 being the highest? | Scaled | 1 | 2 | 3 | 4 | 5
|  |  | How long was your wait time to be seated? | Scaled | 5 minutes | 10 minutes | 15 minutes | 20 minutes | None
|  |  | Do you feel that your wait time was acceptable? | Yes/No | Yes | No
|  |  | Do you have anything you want to share to Sauce and Spoon to make your next dining experience better? | Open-ended | Open-ended

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
POS Implementation Services for Retailers and Wholesale Businesses | POS Implementation - POS Highway | 2022-06-13 | Good framework to follow for tablet implementation
How to Deploy Your New Restaurant Pos Like a Pro | How to Deploy Your New Restaurant Pos Like a Pro – Aptito | 2022-06-13 | More specific ideas relating to tablet implementation
Restaurant reboot | Restaurant reboot (pmi.org) | 2022-06-13 | Story that's similar / aligned to project goals
Previous Project Resource | Week 2 - Historical Project Plan - Google Sheets | 2022-06-19