## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Multiple orders placed while dining | 64% placed multiple orders | Continue advertising menu items on the tablet
Customers | Needs improvement | Customer wait time for tables | 74% mentioned that they waited 11 minutes or more | Check for inefficiencies and baseline against industry standard for similar restaurants
Customers | Needs improvement | Customers receiving correct orders | 72% received orders correct orders | The number of incorrect orders could be lessened by making sure tablet functions properly in taking the orders and that the kitchen receives the correct information.
Project team | Went well | Tablet test lauch went well. | "I think it went pretty well! We got all the tablets installed and working at my location. " Alex | None so far
Project team | Needs improvement | Improve on table turn time | "One area we could still improve is table turn time. We didn’t see as much of a decrease as we wanted to in that area." | Improve on restaurant processes
Project team | Needs improvement | Orders were sent back | "Tickets came through at a good pace and were easy to keep track of. But even though the ticket flow was smooth, there were still orders that got sent back." Zane | Improve kitchen ticket flow operations
Project team | Needs improvement | Technical issues with POS integration and maintenance issues. |  | Update the process manual so that the solution is easy to find next time that issue comes up. In fact, maybe there’s a technical issue that’s affecting ticket accuracy.