## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Omar Mubarak, Project Sponsor | Owner | H | L | 
Peta Tsosie, Project Manager | Project Lead | H | H | 
Deanna Coleman, Director of Operations | Team Member | H | H | 
Carter Ward, Executive Chef | Team Member | M | H | Involved with details and passionately protects kitchen’s best interests
Gilly Tyson, General Manager, North) | Team Member | M | H | 
Alex Schmidt, General Manager (Downtown) | Team Member | M | H | 
Nia Williams, General Manager (Waterfront) | Team Member | L | L | 
Zane Dutchman, Kitchen Manager (North) | Team Member | L | H | 
Larissa Stein, Kitchen Manager (Downtown) | Team Member | L | H | 
Seydou Diallo, Restaurant Technology Consultant | Team Member | M | H | 
Stakeholder Analysis

## Slide 2
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Omar
Owner
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront